## Sheet1
Priority | Item Number | Issue Type | Title | Status | Added by | Assignee | Notes/Comments | Start date | Completion date
P1 | 1 | Project pipeline setup | Project structure creation | Done and closed | Shanjai R | Shanjai R |  | 2024-06-18 | 2024-06-20
P1 | 2 | Project pipeline setup | Creation script addition | Done and closed | Shanjai R | Shanjai R |  | 2024-06-20 | 2024-06-21
P1 | 3 | Project pipeline setup | Deletion script addition | Done and closed | Shanjai R | Shanjai R |  | 2024-06-20 | 2024-06-21
P1 | 4 | Project pipeline setup | common module creation | Done and closed | Shanjai R | Shanjai R | Initial set has been completed | 2024-06-25 | 2024-06-29
P1 | 5 | Project pipeline setup | url_collector common module | Working on it | Shanjai R | Shanjai R |  | 2024-06-25
P1 | 6 | Project pipeline setup | common module modification | Not started | Shanjai R | Shanjai R | we need to create a cache file to store the fetched file in url collector | 2024-06-30